## Slide 1: FHH HealthVault Integration Project
Iteration 5 Review
December 17, 2009

## Slide 2: Iteration 5
What we set out to accomplish:
  Increase Team Velocity
  Complete Action Items from last meeting
  Increase regression test coverage
  Revised UI based on feedback
  Refine Import requirements (risk mitigation)
  Save to Health Vault (Proband only)
All items completed!

## Slide 3
Phase |  | Timeline | Objectives | Status
1 | Inception | 24-Jun 15-Jul | Explore how to enable a user to export family history to HealthVault import family history from HealthVault | Complete
2 | Elaboration | 13-Oct 2-Dec | Implement Communication Specification Establish user interface concepts Develop & Execute Regression Tests Demonstrate executable software | Complete
3 | Development | 3-Dec 16-Dec | Refine Import requirements Develop user interface Increase regression test coverage Save data to HealthVault | Complete
 |  | 17-Dec 31-Dec | Importing and exporting Relatives and Conditions Translate Family History Items | Planning
 |  | 4-Jan 13-Jan | Handling bad data conditions Third party interoperability MS Go-Live Process ASPA Approval Start NCI Appscan process | 
 |  | 14-Jan 26-Jan | Recuit testers Establish beta test environment | 

## Slide 4
Phase |  | Timeline | Objectives | Status
4 | Beta Testing | 27-Jan 7-Feb | Testing with current MFHP users Testing with current HealthVault users Testing with general users | 
5a | Rollout | 8-Feb 15-Feb | deliver to production Provide technical assistance to NCI team | 
5b | Closeout | 16-Feb 10-Mar | Provide technical assistance to NCI team Close out the project | 
Project Timeline

## Slide 5
 | Sprint Start | Delta | Sprint End
Staff | 2 developers 1 tester 1 analyst | + 2 developers +1 info architect | Team of 7
Points | 31.5 | 13.5 | 45
Team Composition & Velocity

## Slide 6
2.3 M5 Burndown Chart

## Slide 7: Actions from last meeting
Action Item | Status
Data export: Need to handle MFHP data not directly supported by HealthVault | Met w/Lowell @ Microsoft Will extend family-history datatype
Data Import: Need to identify and handle HealthVault data not currently supported by MFHP | Developed options for handling HealthVault data not supported in MFHP Can build on existing framework for importing old-style HTM files
User Interface: clients identified new requirements relating to 3rd-party site warning and APSA | brought in Information Architect to revise & extend wireframes

## Slide 8: Test Coverage
Regression coverage (old features)
  45 of 47 features = 95%
  Requirements Traceability Matrix
Remaining 2 features:
  Error messages
    Required fields
    XML error messages
  Alternate flows
    Invalid HealthVault login credentials
    Cancel/Close

## Slide 9: Revised Wireframes
Input from George Komatsoulis (NCI), ASPA, others
Wireframes revised by Andy Evans, Information Architect
  “Leaving FHH web site” warning
  Save .XML file locally now OPTIONAL
  User does NOT enter filename
  Unified look & feel, vocabulary
Available on Gforge
  FHH Save Process WF.pdf
  FHH Open Process Flow - HealthVault.pdf
  FHH Open Process Flow - Local File.pdf

## Slide 10: Requirements for Import
Must recognize and handle HealthVault data MFHP can’t handle natively
  Can reuse some existing HTM import features
    Error message area
    “item requires attention” icons
  Can likely reuse existing “Condition not recognized” features
  Some new interactive dialog may be required
    Relationship
    Other incompletely mapped data values

## Slide 11: Demo: executable software
Save Family History
  Simple case: save proband only
  Visible HealthVault updates
    Family History table entry
    Audit trail history entry
  Hidden HealthVault updates
    Extended data types
    Viewable via X-ray tool
DEMO

## Slide 12: Demo Script: Save to HealthVault
Sign in to HealthVault
Click the Health Information tab
Click the Family History link
  Show that the table is empty
Click on History of Changes
Click on All Changes in the last 30 days
  View latest entries
Start a new browser tab
Go to My Family Health History (demo)
Load a family history with just one person (the proband)
Click on Save Family History button
HealthVault Manager Wizard step 1 appears
Click Cancel; user returned to previous page
Click on Save Family History button

## Slide 13: Demo Script: Save to HealthVault
(continued)
HealthVault Manager Wizard step 2 appears
Click Cancel; user returned to step 1
Repeat & Click Save Now
“Leaving government web site” warning appears
HealthVault login screen appears
Log in to HealthVault
HealthVault Manager successful connection page appears
  “You are now connected to the Microsoft HealthVault account for [accountholder name]. ”
Click on Save to HealthVault
HealthVault manager confirmation message appears – success!

## Slide 14: Demo Script: Save to HealthVault
(continued)
Return to HealthVault
Click on History of Changes
Click on All Changes in the last 30 days
  View new entries recording MFHP input
Click the Health Information tab
Click the Family History link
View the proband’s information in table
  Name & Date of Birth
  Relationship = self
  Condition = none
Use X-Ray to view extended data types
  Weight
  Height

## Slide 15: Iteration 6 Objectives
Continue development of Export Family History
  Save proband’s condition
  Save proband & immediate relatives
  Save entire family
Begin development of Import Family History
  Import previously-exported family history
  Import HealthVault-created family history

## Slide 16: Documents in Gforge
This Sprint Review presentation
  https://gforge.nci.nih.gov/svnroot/fhh/hhs/fhh/trunk/documents/pm/FHH_Sprint5_Review_2009-12-17.pptx
Requirements Traceability Matrix
  https://gforge.nci.nih.gov/svnroot/fhh/hhs/fhh/trunk/documents/test/Automated_Test_Cases_Tracebility_Matrix.xlsx
Revised Wireframes
  https://gforge.nci.nih.gov/svnroot/fhh/hhs/fhh/trunk/documents/ui/
Data Translation map
  https://gforge.nci.nih.gov/svnroot/fhh/hhs/fhh/trunk/documents/requirements/

## Slide 17: Schedule Next Sprint Review
PROPOSED DATE/TIME
  Monday, January 4
  11am – Noon
INVITEES
  Chris Piepenbring
  Leslie Power, Dan Weikart
  Project team

## Slide 18: Agenda
SPRINT PLANNING (2.3 M6)
  Conduct Retrospective
  Iteration 6 Fine-grained Planning

## Slide 19: Sprint Retrospective
SAMALO:
  Same as:
  More of:
  Less of:
2.3 M5 Wiki

## Slide 20: Iteration 6 Planning
Risks
JIRA Tasks

## Slide 21: Risks
Business Impacts
Mitigation Plans

## Slide 22: Proposed JIRA Tasks
Create revised HTML wireframes for Export
Create wireframes for Import
Create HTML wireframes for Import
Write Test Scenarios for HealthVault Export
Develop Export proband & family w/relationships
Develop Export proband & family w/conditions
Develop Export proband & family w/race & ethn.
Write Test Scenarios for HealthVault Import
Develop Import proband w/ gender, race & ethn
Develop Import proband & direct blood relatives
Develop Import proband & all relatives
Write Sprint Review Agenda & Demo Script

## Slide 23: Requirements for Import
Must recognize and handle HealthVault data MFHP can’t handle natively
Reviewed framework for handling import from old-style HTM files
  Can reuse some existing Update page features
    Error message area
    “item requires attention” icons
  Can likely reuse existing “Condition not recognized” features
  Some new interactive dialog required
    Relationship
    Other incompletely mapped data values

## Slide 24: Recognizing Bad Data

## Slide 26: Relationship Data
Name | Relationship to Me | Add History | Update History | Remove Relative
Arthur | Father |  |  | 
Cindi | Aunt |  |  | 
Nancy | Aunt |  |  | 
My name | Self |  |  | 
i
i
i
i
i
Icons here indicate a problem with the Relationship field
i
MFHP only tracks blood relatives. Since Joseph is a friend, this information will not be imported.
MFHP only tracks blood relatives. Since Barbara is a spouse, this information will not be imported.
Info messages here show why certain relatives were not imported

## Slide 27: Relationship Data
Click on the “requires attention” icon to reach dialogs
Is Cindi your …
Maternal Aunt
Paternal Aunt
(Select relative)
Who is the parent of Cousin1 ?
Radio buttons

## Slide 28: Relationship Data
Link to Overview
Link to Spreadsheet