## Slide 1: FHH HealthVault Integration Project
Iteration 6 Review
January 5, 2010

## Slide 2: Iteration 6
What we set out to accomplish:
  Export to Health Vault
    Demographic information
    Diseases/Conditions
  Import from HealthVault
  Convert wireframes to HTML
All completed

## Slide 3
Phase |  | Timeline | Objectives | Status
1 | Inception | 24-Jun 15-Jul | Explore how to enable a user to export family history to HealthVault import family history from HealthVault | Complete
2 | Elaboration | 13-Oct 2-Dec | Implement Communication Specification Establish user interface concepts Develop & Execute Regression Tests Demonstrate executable software | Complete
3 | Development | 3-Dec 16-Dec | Refine Import requirements Develop user interface Increase regression test coverage Save data to HealthVault | Complete
 |  | 17-Dec 4-Jan | Importing and exporting Relatives and Conditions Translate Family History Items | Complete
 |  | 5-Jan 13-Jan | Handling bad data conditions Third party interoperability MS Go-Live Process ASPA Approval Start NCI Appscan process | 
 |  | 14-Jan 26-Jan | Recruit testers Establish beta test environment | 

## Slide 4
Phase |  | Timeline | Objectives | Status
4 | Beta Testing | 27-Jan 7-Feb | Testing with current MFHP users Testing with current HealthVault users Testing with general users | 
5a | Rollout | 8-Feb 15-Feb | deliver to production Provide technical assistance to NCI team | 
5b | Closeout | 16-Feb 10-Mar | Provide technical assistance to NCI team Close out the project | 
Project Timeline

## Slide 5
Team Velocity

## Slide 6
2.3 M6 Burndown Chart

## Slide 7: Actions from last meeting
Action Item | Status
Data export: Finalize data schema for HealthVault extensions | Brian met w/Lowell, MP @ Microsoft Will follow Microsoft recommendations

## Slide 8: Demo: executable software
Save Family History
  In addition to proband, save:
    Demographic info
    Disease/Condition
  Visible HealthVault updates
    Family History table entry
    Audit trail history entry
  Hidden HealthVault updates
    Extended data types
    Viewable via X-ray tool
DEMO

## Slide 9: Demo Script: Save to HealthVault
Sign in to HealthVault
Click the Health Information tab
Click on All Changes in the last 30 days
  View latest entries
Start a new browser tab
Go to My Family Health History (demo)
Load a family history
Click on Save Family History button
HealthVault Manager Wizard step 1 appears
Click on Save Family History button
HealthVault Manager Wizard step 2 appears
Click Save Now
HealthVault login screen appears

## Slide 10: Demo Script: Save to HealthVault
(continued)
Log in to HealthVault
HealthVault Manager successful connection page appears
Click on Save to HealthVault
HealthVault manager confirmation message appears
Return to HealthVault
Click on History of Changes
Click on All Changes in the last 30 days
  View new entries recording MFHP input

## Slide 11: Demo Script: Save to HealthVault
(continued)
Click the Health Information tab
Click the Edit Profile link
View the proband’s information in table
  Name & Date of Birth
  Relationship = self
  Gender
  Condition
Click on Show Optional Information
  Ethnicity
Use X-Ray to view extended data types
  Weight, Height, plus
  Twin status
  Adoption status

## Slide 12: Demo Script: Load from HealthVault
Start a new browser tab
Go to My Family Health History (demo)
Click on Open a Saved History File button
Click on Load from Microsoft HealthVault button
Click on Continue button
Log in to Microsoft HealthVault
Click on Continue button
Click on Load from HealthVault button

## Slide 13: Demo Script: Load from HealthVault
View the previously-saved Family History information
  Name
  Relationship to Me = self
Click on Update History icon
View other previously-saved information
  Gender
  Date of Birth
  Twin status
  Adoption status
  Height, Weight
  Disease / Condition
  Race, Ethnicity

## Slide 14: Requirements
Created & revised Use Cases based on data translation map developed earlier:
  User Imports Translated Data from HealthVault
  User Exports Translated Data to HealthVault
Highlights:
  No pop-ups or Wizard to slow down user
  Informational messages where appropriate
  Display error messages when imported data violates standards
Available on Gforge (links above)

## Slide 15: Information Architecture
Controlled Vocabulary
  Analyzed all application text to derive a list of terms used throughout the application
  Compiled terms into a controlled vocabulary
    Chose the best term for each (or a completely new one that was better than any in use)
  Updated wireframes and application resources in codebase to reflect new terms
  Available on Gforge
    https://gforge.nci.nih.gov/svnroot/fhh/hhs/fhh/trunk/documents/ui/FHH%20Controlled%20Vocab%20initial%20inventory.xlsx

## Slide 16: Information Architecture
Other IA tasks this sprint:
  Authored help text describing the FHH/HealthVault connection and privacy
  Various ongoing adjustments to wireframes in prep for high-fidelity mockups next sprint
  Finalized File Open process wireframes, including authoring text for new screens

## Slide 17: Revised Mockups
Available on Gforge
  Save Process WFs OG.pdf
  FHH Open Process WFs OG – Save to HV.pdf
  FHH Open Process WFs OG – Local File.pdf

## Slide 18: Test Coverage - Regresssion
Regression coverage (old features)
  59 of 60 features = 98%
  Requirements Traceability Matrix
Remaining feature:
  Alternate flows
    Invalid HealthVault login credentials
    Cancel/Close

## Slide 19: Beta Test Planning
Beta Test steps
  Verify Plan
  Schedule beta test
  Prepare beta test environment
  Execute tests
  Review test results
  Identify issues
  Publish test result reports
Available in Gforge:
  FHH Master Test Plan.doc
  FHH BETA Test Cases.xlsx

## Slide 20: Beta Test Team Composition
Tech-savvy testers:
  1 5AM employee not on the FHH team
  1 Incremental employee not on the FHH team
  1. Microsoft employee not on the HealthVault team
  1 Mayo clinic employee/contractor
HeathCare-savvy users
  1 HHS employee/contractor (not one of our stakeholders)
  1 NCI employee/contractor (not one of our stakeholders)
General population users
  friends/relatives recruited by each of the above. Should be:
    mostly female (assumed to be core MFHP users)
    geographically dispersed

## Slide 21: Beta Test Surveys
Web-based survey tool
  Flexible tools for creating and running user surveys
  Common baseline for feedback
  Chose SurveyMonkey.com
Three Beta Test Surveys
  Kickoff survey (recruiting & training beta testers)
  Feedback survey (workhorse – used over & over)
  Wrapup survey

## Slide 22: Iteration 7 Objectives
Implement new wireframes in HTML
Complete development of Export/Import Family History
  Save immediate relatives
  Save entire family
Implement user messages
  Data translation informational messages
  Data error messages
  Handling bad data conditions
Test third-party interoperability (Mayo)
Prepare for rollout
  MS Go-Live Process
  ASPA Approval
  Start NCI Appscan process

## Slide 23: Documents in Gforge
This Sprint Review presentation
  https://gforge.nci.nih.gov/svnroot/fhh/hhs/fhh/trunk/documents/pm/FHH_Sprint6_Review_2010-01-05.pptx
Revised Requirements
  User Imports Translated Data from HealthVault
  User Exports Translated Data to HealthVault
Controlled Vocabulary Initial Inventory
  https://gforge.nci.nih.gov/svnroot/fhh/hhs/fhh/trunk/documents/ui/FHH%20Controlled%20Vocab%20initial%20inventory.xlsx
Wireframes
  Save Process WFs OG.pdf
  FHH Open Process WFs OG – Save to HV.pdf
  FHH Open Process WFs OG – Local File.pdf

## Slide 24: Documents in Gforge
HTML Wireframes
https://design.5amsolutions.com/projects/fhh/save/index.php https://design.5amsolutions.com/projects/fhh/save/downloading.php https://design.5amsolutions.com/projects/fhh/save/manage.php https://design.5amsolutions.com/projects/fhh/save/hv_transition.php https://design.5amsolutions.com/projects/fhh/save/hv.php https://design.5amsolutions.com/projects/fhh/save/hv_post_login.php https://design.5amsolutions.com/projects/fhh/save/hv_success.php https://design.5amsolutions.com/projects/fhh/save/save_hv_canceled.php https://design.5amsolutions.com/projects/fhh/save/save_local_canceled.php
Requirements Traceability Matrix
  https://gforge.nci.nih.gov/svnroot/fhh/hhs/fhh/trunk/documents/test/Automated_Test_Cases_Tracebility_Matrix.xlsx
Beta Test Plan & Surveys
  FHH Master Test Plan.doc
  FHH BETA Test Cases.xlsx
  Kickoff survey
  Feedback survey

## Slide 25: Schedule Next Sprint Review
PROPOSED DATE/TIME
  Thursday, January 14
  11am – Noon
INVITEES
  Chris Piepenbring
  Leslie Power, Dan Weikart
  Project team

## Slide 26: Agenda
SPRINT PLANNING (2.3 M7)
  Conduct Retrospective
  Iteration 7 Fine-grained Planning

## Slide 27: Sprint Retrospective
SAMALO:
  Same as:
  More of:
  Less of:
2.3 M6 Wiki

## Slide 28: Proposed JIRA Tasks
Develop Export proband & direct blood relatives
Develop Export proband & all relatives
Convert Import mockups to HTML wireframes
Integrate HTML wireframes for Import
Develop Import proband & direct blood relatives
Develop Import proband & all relatives
Develop Import data translation info messages
Develop Import data translation error message

## Slide 29: Proposed JIRA Tasks
Create automated tests for XHTML 1.0 validation
Update Export Selenium tests
Create Import Selenium tests
Translate HealthVault help text to Spanish
Review revised application with ASPA
Coordinate Go-Live process with Microsoft
Coordinate NCI Appscan process
Test third-party interoperability (Mayo)
Begin recruiting Beta testers
Write Sprint Review presentation & Demo Script