## Slide 1: FHH HealthVault Integration Project
Iteration 5 Review
Retrospective
Iteration 6 Planning
December 17, 2009

## Slide 2: Agenda
SPRINT REVIEW (2.3 M5)
  Review Actions from last meeting
  Project Timeline
  Demonstrate Iteration 5 Results
SPRINT PLANNING (2.3 M6)
  Proposed Iteration 6 Objectives
  Schedule Sprint Review
  Conduct Retrospective
  Iteration 6 Fine-grained Planning

## Slide 3: Actions from last meeting
(Brian H): Contact Lowell @ Microsoft re: HealthVault changes relating to Race & Ethnicity
  DONE 12/7/09: meeting notes
  must extend family-history datatype
  Custom extensions NOT shown in HealthVault GUI
(Wayne): Review framework for translating old .HTM files formats to the current XML format (FHH-844)
  Subtask of FHH-831: Define requirements for recognizing and handling HealthVault data MFHP can't handle natively.
  Not file translation, but file importing & error checking
  Recommendation: build on this existing framework (more later)

## Slide 4: Project Timeline
Phase |  | Timeline | Objectives | Status
1 | Inception | 24-Jun 15-Jul | Explore how to enable a user to export family history to HealthVault import family history from HealthVault | Complete
2 | Elaboration | 13-Oct 2-Dec | Implement Communication Specification Establish user interface concepts Develop & Execute Regression Tests Demonstrate executable software | Complete
3 | Development | 3-Dec 2-Feb | Refine requirements Translate Family History Items Develop user interface Develop system & regression tests Support CBIT Recruit Testers Establish the Beta test environment | In progress
4 | Beta Testing | 3-Feb 16-Feb | Testing with current MFHP users Testing with current HealthVault users Testing with general users | 
5 | Transition | 17-Feb 10-Mar | Provide technical assistance to NCI team Close out the project | 

## Slide 5: Iteration 5
Phase 2 Objectives
  refine Export requirements
  develop Export
  automate Export tests
  demonstrate Export feature
Iteration 5 Task Themes
  Implement HealthVault authentication
  Implement Save Proband only (baby step)
  Create automated regression tests
  Refine Import requirements (risk mitigation)

## Slide 6: Burndown Charts
31.5 points + 11.5 added = 43
  Fix demo build
  Find way to avoid Selenium sleeps (for consistency on CI server)
  Weight not being set correctly
  Create screen notifying user entering third-party site
16.5 points completed (26.5 left)
2.3 M4 Burndown Chart
2.3 M5 Burndown Chart

## Slide 7: Demonstrate Sprint Results
Demo: executable software
  Connect to HealthVault & save proband
Automated tests
  Performing consistently in improved environment
  Regression, new features tested
Revised wireframes incorporating ASAP input
Requirements for Import
  recognizing and handling HealthVault data MFHP can’t handle natively

## Slide 8: Demo: executable software
FHH-759: Implement HealthVault integration on Save Family History screen (Brian H.)
FHH-827: As a user, after I authenticate with HealthVault, I see a manager screen and have the ability to Save my family health history. (Brian P.)
FHH-767: Implement Save proband only (Brian P.)
DEMO

## Slide 9: Demo Script: Save to HealthVault
Sign in to HealthVault
Click the Health Information tab
Click the Family History link
  Show that the table is empty
Click on History of Changes
Click on All Changes in the last 30 days
  View latest entries
Start a new browser tab
Go to My Family Health History (demo)
Load a family history with just one person (the proband)
Click on Save Family History button
HealthVault Manager Wizard step 1 appears
Click Cancel; user returned to previous page
Click on Save Family History button

## Slide 10: Demo Script: Save to HealthVault
(continued)
HealthVault Manager Wizard step 2 appears
Click Cancel; user returned to step 1
Repat & Click Save Now
HealthVault login screen appears
Log in to HealthVault
HealthVault Manager successful connection page appears
  “You are now connected to the Microsoft HealthVault account for [accountholder name]. ”
Click on Save to HealthVault
HealthVault manager confirmation message appears – success!

## Slide 11: Demo Script: Save to HealthVault
(continued)
Return to HealthVault
Click on History of Changes
Click on All Changes in the last 30 days
  View new entries recording MFHP input
Click the Health Information tab
Click the Family History link
View the proband’s information in table
  Name & Date of Birth
  Relationship = self
  Condition = none
Use X-Ray to view extended data types
  Weight
  Height

## Slide 12: Automated Tests
Regression Tests (Khalid)
  Creating a family history and saving it as a file
  Creating a family history and saving a diagram
  Loading a legacy .htm file
  Adding a relative
  Get Help
New Feature Tests (Khalid)
  Logging in to HealthVault through MFHP.
XHTML 1.0 Transitional validator
  On hold for next sprint

## Slide 13: Test Coverage
Regression coverage (old features)
  19 of 23 features = 83%
  Requirements Traceability Matrix
Total coverage (old & new features)
  Test Summary
  OLD: 9 of 86 points = 5.7%
  NEW: 13 of 71 points = 8.3%
  TOTAL: 22 of 157 points = 14%

## Slide 14: Revised Wireframes
Input from Greg Downing, APSA, others
  “Leaving gov’t web site” warning
  Save .XML file locally now OPTIONAL
Wireframes revised by Andy Evans, Information Architect
  Unified look & feel, vocabulary
  Available on Gforge here.
Next step: create HTML wireframes

## Slide 15: Requirements for Import
Must recognize and handle HealthVault data MFHP can’t handle natively
Reviewed framework for handling import from old-style HTM files
  Can reuse some existing Update page features
    Error message area
    “item requires attention” icons
  Can likely reuse existing “Condition not recognized” features
  Some new interactive dialog required
    Relationship
    Other incompletely mapped data values

## Slide 16: Recognizing Bad Data

## Slide 18: Relationship Data
Name | Relationship to Me | Add History | Update History | Remove Relative
Arthur | Father |  |  | 
Cindi | Aunt |  |  | 
Nancy | Aunt |  |  | 
My name | Self |  |  | 
i
i
i
i
i
Icons here indicate a problem with the Relationship field
i
MFHP only tracks blood relatives. Since Joseph is a friend, this information will not be imported.
MFHP only tracks blood relatives. Since Barbara is a spouse, this information will not be imported.
Info messages here show why certain relatives were not imported

## Slide 19: Relationship Data
Click on the “requires attention” icon to reach dialogs
Is Cindi your …
Maternal Aunt
Paternal Aunt
(Select relative)
Who is the parent of Cousin1 ?
Radio buttons

## Slide 20: Relationship Data
Link to Data Translation field map spreadsheet

## Slide 21: Agenda
SPRINT REVIEW (2.3 M5)
  Review Actions from last meeting
  Project Timeline
  Demonstrate Iteration 5 Results
SPRINT PLANNING (2.3 M6)
  Proposed Iteration 6 Objectives
  Schedule Sprint Review
  Conduct Retrospective
  Iteration 6 Fine-grained Planning

## Slide 22: Iteration 6 Objectives
BUILD SAVE FAMILY HISTORY EXPORT
    xxxx

## Slide 23: Schedule Next Sprint Review
PROPOSED DATE/TIME
  Monday, January 4 ??
  11am – Noon
INVITEES
  Chris Piepenbring, Greg Downing, Kevin Hughes, Greg Feero
  Leslie Power, Dan Weikart
  Project team

## Slide 24: Sprint Retrospective
SAMALO:
  Same as:
  More of:
  Less of:
2.3 M5 Wiki

## Slide 25: Iteration 6 Planning
Risks
JIRA Tasks

## Slide 26: Risks
Business Impacts
Mitigation Plans

## Slide 27: Proposed JIRA Tasks
Schedule Sprint Review
xxx

## Slide 28: Proposed JIRA Tasks
xxx